## Slide 2: Software project planning
After the
finalization
of SRS, we
would
like to
estimate size, cost and development time of the project. Also, in many cases, customer may like to
know the cost and development time even prior to finalization of the SRS.

## Slide 3: Software project planning
In order to conduct a successful software project, we must understand:
Scope of work to be done
The risk to be incurred
The resources required
The task to be accomplished
The cost to be expended
The schedule to be followed

## Slide 4: Software project planning
Software planning begins before technical work starts, continues as the software evolves from concept to reality, and culminates only when the software is retired.
Size estimation
Cost estimation
Development time
Resources requirements
Project scheduling
Fig. 1: Activities during Software Project Planning

## Slide 5: Software project planning
1. | int. sort (int x[ ], int n)
2. | {
3. | int i, j, save, im1;
4. | /*This function sorts array x in ascending order */
5. | If (n<2) return 1;
6. | for (i=2; i<=n; i++)
7. | {
8. | im1=i-1;
9. | for (j=1; j<=im; j++)
10. | if (x[i] < x[j])
11. | {
12. | Save = x[i];
13. | x[i] = x[j];
14. | x[j] = save;
15. | }
16. | }
17. | return 0;
18. | }
Size Estimation
Lines of Code (LOC)
If LOC is simply a count of the number of lines then figure shown below contains 18 LOC .
When comments and blank lines are ignored, the program in figure 2 shown below contains 17 LOC.
Fig. 2: Function for sorting an array

## Slide 6: Software project planning
Furthermore, if the main interest is the size of the program
for specific functionality, it may be reasonable to include executable statements. The only executable statements in figure shown above are in lines 5-17 leading to a count of
13. The differences in the counts are 18 to 17 to 13. One can easily see the potential for major discrepancies for
large programs with many comments or programs written in language that allow a large number of descriptive but non-executable statement. Conte has defined lines of code as:

## Slide 7: Software project planning
“A line of code is any line of program text that is not a
comment or blank line, regardless of the number of statements or fragments of statements on the line. This specifically includes all lines containing program header, declaration, and executable and non-executable statements”.
This is the predominant definition for lines of code used by researchers. By this definition, figure shown above has 17 LOC.

## Slide 8: Software project planning
Function Count
Alan Albrecht while working for IBM, recognized the problem in size measurement in the 1970s, and developed a technique (which he called Function Point Analysis), which appeared to be a solution to the size measurement problem.

## Slide 9: Software project planning
The principle of Albrecht’s function point analysis (FPA) is that a system is decomposed into functional units.
Inputs
Outputs
Enquiries
:
:
:
Internal logical files
:
External interface files
:
information entering the system information leaving the system
requests for instant access to information
information held within the system
information held by other system that is used by the system being analyzed.

## Slide 10: Software project planning
ILF
EIF
User
Other applications
System
Outputs
Inputs
The FPA functional units are shown in figure given below:
User
Inquiries
ILF: Internal logical files EIF: External interfaces
Fig. 3: FPAs functional units System

## Slide 11: Software project planning
The five functional units are divided in two categories:
(i) Data function types
Internal Logical Files (ILF): A user identifiable group of logical related data or control information maintained within the system.
External Interface files (EIF): A user identifiable group of logically related data or control information referenced by the system, but maintained within another system. This means that EIF counted for one system, may be an ILF in another system.

## Slide 12: Software project planning
Transactional function types
  External Input (EI): An EI processes data or control information that comes from outside the system. The EI is an elementary process, which is the smallest unit of activity that is meaningful to the end user in the business.
  External Output (EO): An EO is an elementary process that generate data or control information to be sent outside the system.
  External Inquiry (EQ): An EQ is an elementary process that is made up to an input-output combination that results in data retrieval.

## Slide 13: Software project planning
Counting function points
Functional Units | Weighting factors |  | 
 | Low | Average | High
External Inputs (EI) | 3 | 4 | 6
External Output (EO) | 4 | 5 | 7
External Inquiries (EQ) | 3 | 4 | 6
External logical files (ILF) | 7 | 10 | 15
External Interface files (EIF) | 5 | 7 | 10
Table 1 : Functional units with weighting factors

## Slide 14: Software project planning
Table 2: UFP calculation table
Functional Units |  | Count Complexity |  |  | Complexity Totals |  |  | Functional Unit Totals |  | 
External Inputs (EIs) |  | Low x 3 Average x 4 |  | = = |  |  |  |  |  | 
 |  |  | High x 6 | = |  |  |  |  |  | 
External Outputs (EOs) |  | Low x 4 Average x 5 |  | = = |  |  |  |  |  | 
 |  |  | High x 7 | = |  |  |  |  |  | 
External Inquiries (EQs) |  | Low x 3 Average x 4 |  | = = |  |  |  |  |  | 
 |  |  | High x 6 | = |  |  |  |  |  | 
External logical Files (ILFs) |  | Low x 7 Average x 10 High x 15 |  | = = = |  |  |  |  |  | 
External Interface Files (EIFs) |  | Low x 5 Average x 7 |  | = = |  |  |  |  |  | 
 |  |  | High x 10 | = |  |  |  |  |  | 
Total Unadjusted Function Point Count |  |  |  |  |  |  |  |  |  | 

## Slide 15: Software project planning
The weighting
factors
are identified for all
functional units and multiplied with the functional units accordingly. The procedure for the calculation of Unadjusted Function Point (UFP) is given in table shown above.

## Slide 16: Software project planning
The procedure for the calculation of UFP in mathematical form is given below:
5 3
i1 J 1
Where i indicate the row and j indicates the column of Table 1
Wij : It is the entry of the ith row and jth column of the table 1
Zij : It is the count of the number of functional units of Type i that have been classified as having the complexity corresponding to column j.
UFP  ∑∑ Zij wij

## Slide 17: Software project planning
Organizations that use function point methods develop a criterion for determining whether a particular entry is Low, Average or High. Nonetheless, the determination of complexity is somewhat subjective.
FP = UFP * CAF
Where CAF is complexity adjustment factor and is equal to [0.65 +
0.01 x ΣFi]. The Fi (i=1 to 14) are the degree of influence and are based on responses to questions noted in table 3.

## Slide 18: Software project planning
Table 3 : Computing function points.
2 3
5
4
Rate each factor on a scale of 0 to 5.
0 1
No Influence
Average
Incidental Moderate Significant Essential
Number of factors considered ( Fi )
Does the system require reliable backup and recovery ?
Is data communication required ?
Are there distributed processing functions ?
Is performance critical ?
Will the system run in an existing heavily utilized operational environment ?
Does the system require on line data entry ?
Does the on line data entry require the input transaction to be built over multiple screens or operations ?
Are the master files updated on line ?
Is the inputs, outputs, files, or inquiries complex ?
Is the internal processing complex ?
Is the code designed to be reusable ?
Are conversion and installation included in the design ?
Is the system designed for multiple installations in different organizations ?
Is the application designed to facilitate change and ease of use by the user ?

## Slide 19: Software project planning
Functions points may compute the following important metrics:
Productivity | = | FP / persons-months
Quality | = | Defects / FP
Cost | = | Rupees / FP
Documentation | = | Pages of documentation per FP
These metrics are controversial and are not universally acceptable. There are standards issued by the International Functions Point User Group (IFPUG, covering the Albrecht method) and the United
Kingdom Function Point User Group (UFPGU, covering the MK11 method). An ISO standard for function point method is also being developed.

## Slide 20: Software project planning
Example: 4.1
Consider a project with the following functional units:
Number of user inputs
Number of user outputs Number of user enquiries Number of user files
Number of external interfaces
= 50
= 40
= 35
= 06
= 04
Assume all complexity adjustment factors and weighting factors are average. Compute the function points for the project.

## Slide 21: Software project planning
Solution
5 3
UFP  ∑∑ Zij wij
i1 J 1
UFP = 50 x 4 + 40 x 5 + 35 x 4 + 6 x 10 + 4 x 7
= 200 + 200 + 140 + 60 + 28 = 628
CAF = (0.65 + 0.01 ΣFi)
= (0.65 + 0.01 (14 x 3)) = 0.65 + 0.42 = 1.07 FP = UFP x CAF
= 628 x 1.07 = 672
We know

## Slide 22: Software project planning
Example:4.2
An application has the following:
10 low external inputs, 12 high external outputs, 20 low internal logical files, 15 high external interface files, 12 average external inquiries, and a value of complexity adjustment factor of 1.10.
What are the unadjusted and adjusted function point counts ?

## Slide 23: Software project planning
FP
= 10 x 3 + 12 x 7 + 20 x 7 + 15 + 10 + 12 x 4
= 30 + 84 +140 + 150 + 48
= 452
= UFP x CAF
= 452 x 1.10 = 497.2.
5 3
i1 J 1
UFP  ∑∑ Zij wij
Solution
Unadjusted function point counts may be calculated using as:

## Slide 24: Software project planning
Example: 4.3
Consider a project with the following parameters.
External Inputs:
(a) 10 with low complexity (b)15 with average complexity
(c) 17 with high complexity
External Outputs:
(a) 6 with low complexity (b)13 with high complexity
External Inquiries:
  3 with low complexity
  4 with average complexity
  2 high complexity

## Slide 25: Software project planning
Internal logical files:
(a) 2 with average complexity (b)1 with high complexity
External Interface files:
(a) 9 with low complexity
In addition to above, system requires
  Significant data communication
  Performance is very critical
  Designed code may be moderately reusable
  System is not designed for multiple installation in different organizations.
Other complexity adjustment factors are treated as average. Compute the function points for the project.

## Slide 26: Software project planning
Solution: Unadjusted function points may be counted using table 2
Functional Units | Count | Complexity |  | Complexity Totals |  |  | Functional Unit Totals
External Inputs | 10 15 | Low x 3 Average x 4 | = = | 30 60 |  |  | 
(EIs) | 17 | High x 6 | = |  | 102 | 192 | 
External Outputs (EOs) | 6 0 13 | Low x 4 Average x 5 High x 7 | = = = | 24 0 91 |  |  | 115
External Inquiries (EQs) | 3 4 2 | Low x 3 Average x 4 High x 6 | = = = | 9 16 12 |  |  | 37
External logical | 0 2 | Low x 7 Average x 10 | = = | 0 20 |  |  | 
Files (ILFs) | 1 | High x 15 | = |  | 15 | 35 | 
External Interface Files (EIFs) | 9 0 0 | Low x 5 Average x 7 High x 10 | = = = | 45 0 0 |  |  | 45
 | Total Unadjusted Function Point Count |  |  |  |  |  | 424

## Slide 27: Software project planning
14
∑ Fi
 3+4+3+5+3+3+3+3+3+3+2+3+0+3=41
i1
CAF = (0.65 + 0.01 x ΣFi)
= (0.65 + 0.01 x 41)
= 1.06
FP = UFP x CAF
= 424 x 1.06
= 449.44
Hence FP = 449

## Slide 28
Relative Cost of Software Phases
Software project planning

## Slide 29: Software project planning
Cost to Detect and Fix Faults
200
180
160
140
120
100
80
60
40
20
0
Req
Des
I nt
Cost
Relative Cost to detect and correct fault

## Slide 30: Software project planning
Cost Estimation
A number of estimation techniques have been developed and are having following attributes in common :
Project scope must be established in advance
Software metrics are used as a basis from which estimates are made
The project is broken into small pieces which are estimated individually
To achieve reliable cost and schedule estimates, a number of options arise:
Delay estimation until late in project
Use simple decomposition techniques to generate project cost and schedule estimates
Develop empirical models for estimation
Acquire one or more automated estimation tools

## Slide 31: Software project planning
MODELS
Static, Single Variable Models
Static, Multivariable Models

## Slide 32: Software project planning
C = a Lb
E
= 1.4 L0.93
DOC = 30.4 L0.90
D
= 4.6 L0.26
Effort (E in Person-months), documentation (DOC, in number of pages) and duration (D, in months) are calculated from the number of lines of code (L, in thousands of lines) used as a predictor.
Static, Single Variable Models
Methods using this model use an equation to estimate the desired values such as cost, time, effort, etc. They all depend on the same variable used as predictor (say, size). An example of the most common equations is :
(i)
C is the cost, L is the size and a,b are constants

## Slide 33: Software project planning
E D
= 5.2 L0.91
= 4.1 L0.36
Static, Multivariable Models
These models are often based on equation (i), they actually depend on several variables representing various aspects of the software development environment, for example method used, user participation, customer oriented changes, memory constraints, etc.
The productivity index uses 29 variables which are found to be highly correlated to productivity as follows:
29
  ∑Wi Xi
i1

## Slide 34: Software project planning
Example: 4.4
Compare the Walston-Felix model with the SEL model on a software development expected to involve 8 person-years of effort.
Calculate the number of lines of source code that can be produced.
Calculate the duration of the development. (c)Calculate the productivity in LOC/PY
(d)Calculate the average manning

## Slide 35: Software project planning
Solution
The amount of manpower involved = 8 PY = 96 person-months
(a) Number of lines of source code can be obtained by reversing equation to give:
L = (E/a)1/b
Then
L(SEL) = (96/1.4)1/0.93 = 94264 LOC L(W-F) = (96/5.2)1/0.91 = 24632 LOC.

## Slide 36: Software project planning
Duration in months can be calculated by means of equation D(SEL) = 4.6 (L)0.26
= 4.6 (94.264)0.26 = 15 months D(W-F) = 4.1 L0.36
= 4.1(24.632)0.36 = 13 months
Productivity is the lines of code produced per person/month (year)
P(SEL)  94264  11783 LOC / Person  Years
8
P(W  F )  24632  3079 LOC / Person  Years
8

## Slide 37: Software project planning
(d) Average manning is the average number of persons required per month in the project.
M (SEL)  96 P M  6.4Persons
15 M
M (W  F )  96 P M  7.4Persons
13 M

## Slide 38: Software project planning
Basic Intermediate Detailed
Model proposed by
B. W. Boehm’s through his book
Software Engineering Economics in 1981
The Constructive Cost Model (COCOMO)
Constructive Cost model (COCOMO)

## Slide 39: Software project planning
COCOMO applied to
Semidetached mode
Embedded mode
Organic mode

## Slide 40: Software project planning
Table 4: The comparison of three COCOMO modes
Mode | Project size | Nature of Project | Innovation | Deadline of the project | Development Environment
Organic | Typically 2-50 KLOC | Small size project, experienced developers in the familiar environment. For example, pay roll, inventory projects etc. | Little | Not tight | Familiar & In house
Semi detached | Typically 50-300 KLOC | Medium size project, Medium size team, Average previous experience on similar project. For example: Utility systems like compilers, database systems, editors etc. | Medium | Medium | Medium
Embedded | Typically over 300 KLOC | Large project, Real time systems, Complex interfaces, Very little previous experience. For example: ATMs, Air Traffic Control etc. | Significant | Tight | Complex Hardware/ customer Interfaces required

## Slide 41: Software project planning
Basic Model
Basic COCOMO model takes the form
bb
E  ab (KLOC)
db
D  cb (E)
where E is effort applied in Person-Months,
and D is the
development time in months. The coefficients ab, bb, cb and db are given in table 4 (a).

## Slide 42: Software project planning
Software Project | ab | bb | cb | db
Organic | 2.4 | 1.05 | 2.5 | 0.38
Semidetached | 3.0 | 1.12 | 2.5 | 0.35
Embedded | 3.6 | 1.20 | 2.5 | 0.32
Table 4(a): Basic COCOMO coefficients

## Slide 43: Software project planning
When effort and development time are known, the average staff size to complete the project may be calculated as:
Average staff size (SS )  E Persons
D
the productivity
level
may be
When project size is known, calculated as:
Productivity (P)  KLOC KLOC / PM
E

## Slide 44: Software project planning
Example: 4.5
Suppose that a project was estimated to be 400 KLOC. Calculate the effort and development time for each of the three modes i.e., organic, semidetached and embedded.

## Slide 45: Software project planning
Solution
The basic COCOMO equation take the form:
bb
E  ab (KLOC)
db
D  cb (E)
Estimated size of the project = 400 KLOC
(i) Organic mode
E = 2.4(400)1.05 = 1295.31 PM
D = 2.5(1295.31)0.38 = 38.07 PM

## Slide 46: Software project planning
Semidetached mode
E = 3.0(400)1.12 = 2462.79 PM
D = 2.5(2462.79)0.35 = 38.45 PM
Embedded mode
E = 3.6(400)1.20 = 4772.81 PM
D = 2.5(4772.8)0.32 = 38 PM

## Slide 47: Software project planning
Example: 4.6
A project size
of 200 KLOC
is to
be developed. Software
development team has average experience on similar type of projects. The project schedule is not very tight. Calculate the effort, development time, average staff size and productivity of the project.

## Slide 48: Software project planning
Solution
The semi-detached mode is the most appropriate mode; keeping in view the size, schedule and experience of the development team.
E = 3.0(200)1.12 = 1133.12 PM
D = 2.5(1133.12)0.35 = 29.3 PM
Hence
Average staff size (SS )  E Persons
D
 1133.12  38.67Persons
29.3

## Slide 49: Software project planning
Productivity
 KLOC  200  0.1765 KLOC / PM E 1133.12
P  176 LOC / PM

## Slide 50: Software project planning
Intermediate Model
Cost drivers
(ii)
Product Attributes
  Required s/w reliability
  Size of application database
  Complexity of the product Hardware Attributes
  Run time performance constraints
  Memory constraints
  Virtual machine volatility
  Turnaround time

## Slide 51: Software project planning
Personal Attributes
  Analyst capability
  Programmer capability
  Application experience
  Virtual m/c experience
  Programming language experience
Project Attributes
  Modern programming practices
  Use of software tools
  Required development Schedule

## Slide 52: Software project planning
Multipliers of different cost drivers
Cost Drivers | RATINGS |  |  |  |  | 
 | Very low | Low | Nominal | High | Very high | Extra high
Product Attributes |  |  |  |  |  | 
RELY | 0.75 | 0.88 | 1.00 | 1.15 | 1.40 | --
DATA | -- | 0.94 | 1.00 | 1.08 | 1.16 | --
CPLX | 0.70 | 0.85 | 1.00 | 1.15 | 1.30 | 1.65
Computer Attributes |  |  |  |  |  | 
TIME | -- | -- | 1.00 | 1.11 | 1.30 | 1.66
STOR | -- | -- | 1.00 | 1.06 | 1.21 | 1.56
VIRT | -- | 0.87 | 1.00 | 1.15 | 1.30 | --
TURN | -- | 0.87 | 1.00 | 1.07 | 1.15 | --

## Slide 53: Software project planning
Table 5: Multiplier values for effort calculations
Cost Drivers | RATINGS |  |  |  |  | 
 | Very low | Low | Nominal | High | Very high | Extra high
Personnel Attributes |  |  |  |  |  | 
ACAP | 1.46 | 1.19 | 1.00 | 0.86 | 0.71 | --
AEXP | 1.29 | 1.13 | 1.00 | 0.91 | 0.82 | --
PCAP | 1.42 | 1.17 | 1.00 | 0.86 | 0.70 | --
VEXP | 1.21 | 1.10 | 1.00 | 0.90 | -- | --
LEXP | 1.14 | 1.07 | 1.00 | 0.95 | -- | --
Project Attributes |  |  |  |  |  | 
MODP | 1.24 | 1.10 | 1.00 | 0.91 | 0.82 | --
TOOL | 1.24 | 1.10 | 1.00 | 0.91 | 0.83 | --
SCED | 1.23 | 1.08 | 1.00 | 1.04 | 1.10 | --

## Slide 54: Software project planning
Intermediate COCOMO equations
Project | ai | bi | ci | di
Organic | 3.2 | 1.05 | 2.5 | 0.38
Semidetached | 3.0 | 1.12 | 2.5 | 0.35
Embedded | 2.8 | 1.20 | 2.5 | 0.32
Table 6: Coefficients for intermediate COCOMO
* EAF
bi
E  ai (KLOC)
di
D  ci (E)